## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43037
Planning | 2017-10-29 | 2017-10-31 | 2 | 2 | 0 | 100%
setup the Github repository | 2017-10-29 | 2017-10-30 | 1 | 1 | 0 | 100%
Setup the version controller(git) | 2017-11-01 | 2017-11-02 | 1 | 1 | 0 | 100%
Create a project in the Github | 2017-11-03 | 2017-11-04 | 1 | 1 | 0 | 100%
Give the descripiton of the project | 2017-11-04 | 2017-11-05 | 1 | 1 | 0 | 100%
Define the requirements and functions of the project | 2017-11-21 | 2017-12-15 | 24 | 24 | 0 | 100%
Make Breakdown structure | 2017-11-05 | 2017-11-07 | 2 | 2 | 0 | 100%
Make Software development cycle | 2017-11-08 | 2017-11-09 | 1 | 1 | 0 | 100%
Define the boundary of the problems | 2017-11-29 | 2017-12-11 | 12 | 12 | 0 | 100%
Make Deployment diagram | 2017-12-11 | 2017-12-19 | 8 | 8 | 0 | 100%
Make All the diagrams | 2017-12-12 | 2017-12-21 | 9 | 9 | 0 | 100%
Code | 2017-12-21 | 2017-12-22 | 1 | 1 | 0 | 100%
Write the report | 2017-12-22 | 2017-12-24 | 2 | 2 | 0 | 100%